## Sheet1
Week | <component> | Complexity (LOW 1 - 5 HIGH)
2023-01-01 | Overall Planning (PM, agile board setup) | 1
2023-01-08 | Azure Cloud and GitHub setup (connected securely) | 2
2023-01-15 | Test code development | 2
2023-01-22 | GitHub Actions (CI) with test code | 3
2023-01-29 | Python (ML Flask) Application code | 5
2023-02-05 | Local deployment and testing of application | 3
2023-02-12 | DevOps organization and project setup in Azure | 3
2023-02-19 | DevOps Pipeline setup (CD) | 4
2023-02-26 | DevOps Pipeline (CD) integration with GitHub Actions (CI) | 5
2023-03-05 | CI/CD functionality testing | 5
2023-03-12 | CI/CD - application code changes, testing and deployment to Azure WebApp | 4
2023-03-19 | Proof of concept (application changes triggering reintegration and new deployment) | 5
Goals
Project Management Plan completed
CI environment set up
CD environment set up
semi-automated app build and deployment to Azure WebApp